## Slide 1
Global Job Profile Modernization
HR Transformation Team, SAP
INTERNAL

## Slide 2: Objective
Modernize and simplify our global job profile framework to enable consistent talent decisions, improve workforce transparency, and support strategic workforce planning at scale.
This initiative replaces legacy, fragmented job architectures with a streamlined, future-ready structure aligned to business strategy and market benchmarks.

## Slide 3: Progress to Date

## Slide 4: What's Been Accomplished So Far
- Global framework design completed: Defined a simplified job architecture with standardized job families, levels, and naming conventions across all regions and business units.
- Stakeholder alignment secured: Completed engagement with HR leadership, Compensation, Talent Acquisition, and select business leaders to validate design principles and governance model.
- Data assessment finalized: Audited existing job profiles across regions, identifying redundancies, inconsistencies, and gaps — reducing total profile count by approximately 40%.
- Technology readiness confirmed: Partnered with HR Technology/Workday team to confirm system configuration requirements and integration pathway.
- Pilot completed: Successfully tested the new framework in [pilot business unit/region], incorporating feedback into the final design.

## Slide 5: What's Next

## Slide 6: Next 90 Days: Key Milestones Milestones & Target Dates
Chart: 
| Finalize role mapping | Manager comms & change readiness | Regional deployment (Wave 1) | Compensation benchmarking | Feedback checkpoint
 | 4 | 5 | 8 | 10 | 12

## Slide 7: Risk Management

## Slide 8: Key Risks & Mitigation
- Change resistance from managers: Structured change management plan with targeted toolkits and leadership-led communications
- Regional regulatory/works council requirements: Early engagement with local labor counsel and employee reps
- Data quality gaps in legacy systems: Dedicated data stewards and validation checkpoints
- Competing HR transformation priorities: Aligned with HR tech roadmap and secured dedicated project resourcing

## Slide 9: Leadership Support Needed

## Slide 10: Leadership Ask
1. Visible executive sponsorship: Champion the change in leadership forums and town halls.
2. Hold business leaders accountable for timely completion of role mapping.
3. Protect project resourcing: Maintain dedicated team allocation and prioritize this initiative.
4. Empower the project team: Decision rights to resolve escalations within a 5-day SLA.

## Slide 11
HR Transformation Team
user@example.com